## Sheet1
Tasks | Start Date | End Date: | Part of Milestone #:
Research and communicate basic steps to create unity game | 2022-12-15 | 2023-01-10 | 1
Research basic steps to create unreal engine game | 2022-12-15 | 2023-01-10 | 1
Develop empty sandbox | 2023-01-03 | 2023-01-17 | 1
Controllers are giving input with basic movement. | 2023-01-10 | 2023-01-17 | 1
Build Test 1: Regular build tests to test pre-decided packaged features | 2023-01-10 | 2023-01-17 | Milestone 1 Finished
Create ability to draw with controller | 2023-01-17 | 2023-02-07 | 2
Create the ability to extrude shapes | 2023-01-17 | 2023-02-07 | 2
Create ability to delete objects | 2023-01-17 | 2023-02-07 | 2
Develop UI tool selector | 2023-01-17 | 2023-02-07 | 2
Build Test 2: Regular build tests to test pre-decided packaged features | 2023-02-07 | 2023-02-08 | Milestone 2 finished
Create ability to interact with objects | 2023-02-08 | 2023-02-20 | 3
Create preset object menu | 2023-02-08 | 2023-02-20 | 3
Create the ability to undo and redo actions | 2023-02-08 | 2023-02-20 | 3
Create ability to scale objects based on input from user | 2023-02-20 | 2023-03-04 | 3
Create ability to scale player based on input from user | 2023-02-20 | 2023-03-04 | 3
Create the ability to change the color of markers | 2023-02-20 | 2023-03-04 | 3
Build Test 3: Regular build tests to test pre-decided packaged features | 2023-03-04 | 2023-03-05 | Milestone 3 finished
Create ability to export shapes into 3d file format | 2023-03-05 | 2023-03-15 | 4
Create ability to view save states | 2023-03-05 | 2023-03-15 | 4
Create ability to make new environment | 2023-03-05 | 2023-03-15 | 4
Create ability to load in previously made environments | 2023-03-15 | 2023-03-30 | 4
Create ability to save states/version control | 2023-03-15 | 2023-03-30 | 4
Implement player movement tool with headset | 2023-03-15 | 2023-03-30 | 4
Build Test 4: Regular build tests to test pre-decided packaged features | 2023-03-30 | 2023-03-31 | Milestone 4 Finished
Create the ability to bind objects to other objects | 2023-03-31 | 2023-04-14 | 5
Create ability to replicate drawings | 2023-03-31 | 2023-04-14 | 5
Create ability to cut objects | 2023-03-31 | 2023-04-14 | 5
Create ability to add/modify edge loops | 2023-03-31 | 2023-04-14 | 5
Build Test 5: Regular build tests to test pre-decided packaged features | 2023-04-14 | 2023-04-14 | 5
Testing
Module Tests: each task is tested during development by developer | N/A | N/A | 1, 2, 3, 4, 5
Build Tests: each task is tested in groups based on milestone completion | N/A | N/A | 1, 2, 3, 4, 5